## Sheet1
Project Name | Text Recognition using ML
Project Guide | Prof Maindargi L C.
Team members: | Prathmesh Yakkaldevi | 55
| Akshay Manekari | 56
| Saitarun Patel | 57
| Shahrukh Shaikh | 58
| Shrikant Gullapalli | 59
Date | Task | Responsible | Completion | Comment
2020-07-18 | Team formation and selection of Team leader. | - | 2020-07-21 | Team leader selected by casting votes
2020-08-24 | Project selection | - |  | Everyone put their own idea, discussed about each idea, selected most suitable.
Prathmesh, Akshay, Tarun started to learn about Machine Learning; Shahrukh, Shrikant started to learn about GUI
2020-09-04 | Project abstract | Sharukh | 2020-09-05 | Changes needed
2020-09-05 | Changes in Project abstract | Sharukh | 2020-09-08 | Submitted
2020-12-28 | PPT presentation | ALL | 2020-12-28
2020-12-29 | Project Report | ALL | 2020-12-29
2021-02-15 | single word per image data genration | Akshay | 2021-02-17
2021-02-15 | Basic Design of GUI Created | Shahrukh
2021-02-18 | single word per image data labelling | Prathmesh
2021-02-19 | Generation of Data set including word gen,mid point calulation | Akshay | 2021-03-01 | Although,it wasn't used later in the project
2021-02-20 | Python Selected as Platform | Shahrukh
2021-02-20 | Trained models to predict Word position | Tarun
2021-02-21 | Basics of Tkinter | Shahrukh | 2021-03-08
Group Meeting to change method
Group Meeting: decide input and output of Each Task
2021-03-03 | Need of a B/W image converter. |  |  | Discussion on plausible ways to tackle B/W image conversion process.
2021-03-04 | Work on B/W image converter begins | Akshay
2021-03-05 | Trained models to recognise character | Tarun
2021-03-05 | Design pseudocode of charctor extraction | Prathmesh
2021-03-06 | Static B/W image converter completion | Akshay
2021-03-08 | Work on dynamic image converter begins | Akshay
2021-03-08 | Started Learing Python Liabry | Shrikant
2021-03-10 | Selection of an approach among other approaches for B/W conversion | Akshay | 2021-03-10
2021-03-10 | Implemet pseudocode of charctor extraction | Prathmesh
2021-03-15 | Working GUI model Developed | Shahrukh
2021-03-20 | Completion of B/W converter(Image wise) | Akshay
2021-03-22 | Work on slice-wise conversion code | Akshay
2021-03-25 | Coding of slice-wise image conv. | Akshay | 2021-03-25
2021-03-25 | Cropping Code implimentation started | Shrikant
2021-03-28 | Problems with slice-wise conv. | Akshay
2021-03-30 | Need of pumping up the internal variables | Akshay | 2021-04-05
2021-04-01 | Merging Rest Project with GUI | sharukh
2021-04-03 | Workspace and other Improvements in GUI | Shahrukh
2021-04-04 | Tested various types of images croped | Shrikant
2021-04-06 | Backup Images Feature added | Shahrukh
2021-04-13 | Trained 4 models: "SmallAZVersion0", "SmallAZVersion1", "SmallAZVersion2", "SmallAZVersion3". | Tarun | 2021-04-13 | Accuracy of 90.74%, 92.74%, 94.09% and 93.95% respectively.
2021-04-14 | Testing of different Threshold values: 2.5, 5.0, 7.5, 10.0 | Tarun | 2021-04-20 | Choose "SmallAZVersion2" with threshold 5.0 to gain accuracy of 90.37%
2021-04-15 | Adding code to fit image on Screen
2021-04-19 | Solve problem of distorted Char(Make Char smooth) of charctor extraction code | Prathmesh
2021-04-22 | Solve problem of Two characrors in charactor Image | Prathmesh
2021-05-18 | PPT created | ALL
2021-05-20 | Technical paper on project | ALL
2021-05-22 | Tasked every team member to provide data of their contribution for Project report | Tarun, Akshay, Prathmesh, Shahruk, Shrikant. | 2021-05-23 | Every member submitted their data to Tarun.
2021-05-22 | GUI Documentation/Report Writing | ALL | 2021-05-23
2021-05-23 | Remerging GUI with rest of Project | Shahrukh | 2021-05-23
2021-05-23 | Combined Project report | Tarun | 2021-05-23 | Submitted to Maindargi sir in pdf and doc format by Prathmesh.
2021-05-25 | Internal Project Presentation | ALL | 2021-05-25